## Task
Name | Task | Deadline | Status | Note
Nguyễn Ngọc Thanh Hải | Initiate project | 23h 14/10/2014 | done | Hello world Project with completed config
| Game Play and Function | 23h 15/10/2014 | done
| Database version 1 | 23h 15/10/2014 | done
| Builder partern vs Façade partern | 23h 14/10/2014 | done | complete slide
| Web Interface | 23h 20/10/2014
| Web js game | 23h 21/10/2014
Trần Quang Phúc | Research + Demo Java Websocket | 23h 15/10/2014 | remove
| Builder partern | 23h 14/10/2014 | done | complete slide
| Code BLL | 23h 22/10/2014 |  | referenced Requirement BLL functions at file Servlet.xlsx
Hà Võ Minh | Iterator partern | 23h 14/10/2014 | done | complete silde
| Code Dal | 23h 22/10/2014
Nguyễn Toàn Thắng | Document Template | 23h 15/10/2014 | done
| Facade partern | 23h 14/10/2014 | done | complete slide
| Code Servlet | 23h 22/10/2014 |  | referenced file Servlet.xlsx

## Dashboard
Time
T | W | T | F | S | S | M | T | W | T | F | S | S | M
14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Progess Bar
kick off | research + document |  |  | code
100% | 90% |  |  | 5%
test + fix bug